WESTERN PACIFIC UNIVERSITY

CMN224 / CMP224 Software Engineering — Week 6

Estimation Workshop

In session · individual work on YOUR Task 2 client · output IS Task 2 sections 2.1–2.3

| Item | Details |
| --- | --- |
| Linked to | Week 6 lecture — Estimation & the Work Schedule (ULO3) |
| Bring | Your Week 5 architecture (Lab 4) and your Week 3 increment plan (Lab 3) |
| Time | 120 minutes: 30 breakdown · 35 estimate · 20 calendar · 25 schedule · 10 commit |
| Submission | Submit this worksheet to Moodle AND committed to week06/ in your Git portfolio |
| Counts toward | Nothing directly — but it drafts 15 of the marks in Task 2 |
| You cannot estimate what you have not designed. Work from your Week 5 package and deployment diagrams: each component is a natural work item. If you did not complete Lab 4, do a rough breakdown from your SRS instead and note that as an assumption. |  |

Part A — Break down Increment 1 (30 min)

Take Increment 1 only from your Week 3 plan — the slice that is independently usable. Decompose it until every task is between 2 and 16 hours. Aim for 8–12 tasks.

Do not forget: unit tests · durability/failure testing · code review · client review and rework · documentation · installation and handover. In the worked example, these came to 39% of the total.

Part B — Estimate each task (35 min)

For each task, give three numbers in hours. O = everything goes right. M = a normal day. P = the realistic bad case (about one time in twenty), not the apocalypse. E = expected time(This is the most realistic estimate of how long a task will take after considering best-case, normal, and worst-case scenarios). And SD = Standard Deviation (this measures the uncertainty or risk in your estimate).

E = ( O + 4M + P ) ÷ 6          SD = ( P − O ) ÷ 6

Increment 1: Student registration, student records, login system, search functionality.

| # | Task | O | M | P | E | SD | Assumption behind it |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project setup & Git repository | 2 | 3 | 6 | 3.33 | 0.67 | Development tools already installed |
| 2 | Database design for student records | 4 | 6 | 10 | 6.33 | 1.00 | Requirements remain stable |
| 3 | Student registration form | 4 | 8 | 12 | 8.00 | 1.33 | No major UI changes |
| 4 | Student record management | 6 | 10 | 16 | 10.33 | 1.67 | CRUD operations only |
| 5 | Login & authentication | 4 | 6 | 12 | 6.67 | 1.33 | Single-user role initially |
| 6 | Student search functionality | 3 | 5 | 10 | 5.50 | 1.17 | Search by ID and name only |
| 7 | Unit testing | 3 | 5 | 8 | 5.17 | 0.83 | Core functions tested |
| 8 | Power failure testing | 2 | 4 | 8 | 4.33 | 1.00 | Testing environment available |
| 9 | Client review & rework | 3 | 6 | 12 | 6.50 | 1.50 | Client available for review |
| 10 | Documentation & handover notes | 2 | 4 | 8 | 4.33 | 1.00 | Basic documentation only |

Total E = 60.49 h          Combined SD = √(sum of SD²) = 4.14 h

Note: the combined SD is NOT the sum of the SDs — square each one, add them, then take the square root. Risks partly cancel out.

Increment 2: Payment recording, instalment tracking, balance calculation, receipt printing.

E = ( O + 4M + P ) ÷ 6          SD = ( P − O ) ÷ 6

| # | Task | O | M | P | E | SD | Assumption behind it |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Payment Recording | 3 | 5 | 7 | 5.0 | 0.67 | Database structure exists |
| 2 | Instalment tracking | 4 | 6 | 9 | 6.17 | 0.83 | Instalment schedules and due dates are predefined. |
| 3 | Balance calculation | 2 | 4 | 6 | 4.0 | 0.67 | Calculation rules are fixed and straightforward. |
| 4 | Receipt Management | 2 | 3 | 5 | 3.17 | 0.50 | Receipt templates and a printing library are available. |
| 5 | Reporting and monitoring | 3 | 5 | 8 | 5.17 | 0.83 | Historical transaction data is available for reports. |
| 6 | User Management | 4 | 6 | 8 | 6.0 | 0.67 | Authentication and user roles follow standard practices. |
| 7 | Notification Management | 2 | 4 | 7 | 4.17 | 0.83 | Email/SMS APIs are already configured and accessible. |

Total E = 33.68_ h          Combined SD = √(sum of SD²) = _1.91__ h

Increment 3: Reports, summary dashboards, backup and synchronization features.

E = ( O + 4M + P ) ÷ 6          SD = ( P − O ) ÷ 6

| # | Task | O | M | P | E | SD | Assumption behind it |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Reports Management | 4 | 6 | 9 | 6.17 | 0.83 | Historical payment and instalment records are available, accurate, and accessible for generating reports. |
| 2 | Summary dashboard | 3 | 5 | 8 | 5.17 | 0.83 | Dashboard metrics are calculated from reliable and up-to-date database records. |
| 3 | Backup and Synchronization Management | 5 | 8 | 12 | 8.17 | 1.17 | Backup servers, storage devices, and network services are operational and properly configured. |
| 4 | Data Recovery Management | 4 | 6 | 10 | 6.33 | 1.0 | Regular backups have been completed, and recovery procedures have been tested previously. |
| 5 | User Activity Management | 3 | 5 | 8 | 5.17 | 0.83 | User authentication mechanisms are functioning, and all activities are logged automatically. |
| 6 | System Maintenance | 4 | 7 | 10 | 7 | 1.0 | Maintenance resources, software updates, and technical support are available throughout the project lifecycle. |

Total E = 38.01_ h          Combined SD = √(sum of SD²) = _2.33__ h

Part C — Convert to a calendar (20 min)

| Question | Your answer |
| --- | --- |
| How many PRODUCTIVE hours per week can you truly give this project? (Count your other units.) | 26hours (2hr on weekdays and 3hrs on weekends) |
| Total E ÷ productive hours per week = how many weeks? | 132.18 divided by 26 hrs = 5.08weeks |
| Same calculation using E − SD and E + SD → your honest range | (132.18 - 8.381) / 26 = 4.76 weeks (132.18 + 8.381) /26 = 5.41 weeks |
| Which PNG factors will stretch this? (client availability, travel, power, term dates, holidays) | Unreliable electricity, school staff availability, and assignment and exam workload. |
| Adjusted finish, stated as a range | 5 - 6 weeks |

Part D — Build the schedule (25 min)

Lay out all three increments with client-visible milestones. A milestone must be something your client could verify themselves — “the bursar records a real payment and prints a receipt”, never “backend complete”.

| Increment | What it delivers | Milestone the client can see | Weeks |
| --- | --- | --- | --- |
| 1 | Login, student registration, student records, search | Office staff successfully register and search for students | Weeks 1-2 |
| 2 | Payments, instalments, balance calculations, receipts | Bursar records a payment and prints a receipt | Weeks 3-4 |
| 3 | Reports, dashboards, backup and synchronization | School generates reports and recovers data after outages | Weeks 5-6 |

Part E — Commit (10 min)

- Put this worksheet into week06/ in your portfolio.

git add week06/

git commit -m "Add increment 1 estimate and delivery schedule"

Reference — the worked example from the lecture

Kina Ridge fee system, Increment 1. Use it to check your arithmetic method, not to copy numbers.

| Task | O | M | P | E | SD |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project + repo setup | 2 | 3 | 6 | 3.33 | 0.67 |  |
| Data model + local database | 4 | 6 | 12 | 6.67 | 1.33 |  |
| Payment entry screen | 6 | 10 | 20 | 11.00 | 2.33 | widest spread |
| Receipt numbering + printing | 4 | 8 | 16 | 8.67 | 2.00 |  |
| Authorisation (bursar / head) | 3 | 5 | 10 | 5.50 | 1.17 |  |
| Unit tests | 4 | 6 | 10 | 6.33 | 1.00 | non-coding |
| Power-failure durability test | 2 | 4 | 10 | 4.67 | 1.33 | non-coding |
| Client review + rework | 3 | 6 | 14 | 6.83 | 1.83 | non-coding |
| Install + handover at school | 2 | 4 | 10 | 4.67 | 1.33 | non-coding |
| TOTAL |  |  |  | 57.67 | 4.58 |  |

Sum of “most likely” alone = 52.0 h. PERT expected = 57.7 h — the 11% gap is optimism made visible. Honest range = 53–62 h. Non-coding work = 22.5 h, 39% of the job. At 10 productive hours a week that is about 5.8 weeks.